## Instructions
Recommendation is to select the appropriate categories and questions applicable per study design as variations will occur due to overall strategy (ex. Hybrid models verse full Decentralized Clinical Trials (DCT)). Template to be a supplement tool for risk assessment completion in which DCT is an element of the overall study design. Acknowledgement: The present DCT Risk Assessment Considerations workbook was inspired by TransCelerate Biopharma INC. Risk Assessment Catagorization Tool (RACT)
Label | Column | Definition
Category | B | The DCT Risk Assessment Template consists of thirteen categories (highlighted in grey)
Objective | C | Linked to category column summarizes key objective for each section (highlighted in grey).
Assessment Criteria | D | Questions engage cross-function teams to evaluate and identify risk.
Considerations | E | Support the assessment criteria with additional considerations for risk identification.
Impact, Probability, and Detectability | F, G, H, | Overall scoring of the risk should follow companies standard practices and if no standard practices are established the recommendation is to use Transcelerate RACT ranking strategy. A score will be associated with this: difficult to detect (3), medium to detect (2), easy to detect (1). After completion of each of the separate questions, a score is assigned to each category (gray lines). - this does not have to be an average but should be based on the cross-functional team discussion considering the importance of the underlying questions specific to this trial.
Category Risk Score | I | A category risk score is calculated for each of the risk categories (gray lines). This is calculated as the product of impact, probability, detectability at the category level. This does not have to be an average but should be based on the cross-functional team discussion considering the importance of the underlying questions specific to this trial.
Weighting | J | Weighting: depending on trial-specific requirements, there is an opportunity to rank the importance of the categories by assigning a weight to each category: default is 1.0. If a certain category is of lesser importance, it can be given a lower weight (ranging from 0.1 to 1.0 - 0 should not be used).
Mitigation Strategies | K | Considerations for mitigation strategies have been provided as examples.

## Risk Assessment
[5 empty] | Overall Risk Score |  |  | #VALUE!
Assessment # | Category | Objective | Assessment Criteria / Questions for Discussion | Considerations | Impact | Probability | Detectability | Total Score | Category Weighting 0.1 - 1.0 (summary rating only 1.0 is default) | Mitigation Strategies
1 | General IT and Systems Consideration | Consider connectivity and robust infrastructure of the DCT network |  |  | Medium (2) | Medium (2) | Medium to detect (2) | 8 | 1
1.1 |  |  | Is there a mechanism in place to inform and educate trial participants on a DCT and the process? | Need to evaluate if there is additional burden on the participant for the trial design using technology. How will participants be educated on the use of technology to ensure compliance? What are the training requirements? | [5 empty] | Paper back up option for if a device fails
1.2 |  |  | Is there a mechanism in place to inform and educate site staff on a DCT and the process? | Training requirement, consideration to be made due to the nature of the trial and site performing activities remotely.
1.3 |  |  | Is there a mechanism in place to inform and ethics and IRBs on a DCT and the process? | Determine the timing of submissions and what documentation is needed for submissions as this will vary per country.
1.4 |  |  | Have all the stakeholders been identified to allow for adequate time to create the appropriate training materials prior to key milestones? | Have Trial participants, sites, sponsors, vendors, ethics committees, couriers, CROs etc been identified and training available for all relevant users pertinent to the process, role and systems being used.
1.5 |  |  | Is the an appropriate infrastructure in place to support the DCT based on geography? | Is there an architectural/infrastructural document that provides an overview of the DCT design? Is there appropriate infrastructure to support the DCT based on geography? This could cover on premise, on site, or centralized infrastructure for example software as a service where multiple sites can leverage the process and technology.
1.6 |  |  | Is there appropriate documentation that provides an overview of the DCT data flow, collection and overall data strategy? | Requirement for a overall data strategy to support oversight. Requirement for a data flow diagram, considering who owns the data, who can query the data, how investigator retains control and access during and after study conclusion
1.7 |  |  | Will there be connectivity issues for the participants and the site? | When might the trial participant need to access the applications, at home, at work or external to the home i.e. need for Wi-Fi and roaming 4G/5G, foreign places.
1.8 |  |  | Does the site have sufficient bandwidth and connectively to manage data and interactions and engagement via remote means for all user? | May need to update bandwidth and connectively capabilities to manage multiple participants and geographies. Are the systems scalable.
1.9 |  |  | Are gaps created due to lack of interface between DCT systems? | Ideally there needs to be common data models and the typically terminologies are not the same, leading to misinterpretation. This can lead to data integration across applications into EMR/eCRF etc. Challenge no common architecture.
1.1 |  |  | Will the process leverage multiple vendors process and technologies? If yes then how does data get transferred between the systems? Can vendors share data through an open ADI? | Ensuring the vendors have the clinical grade processes and controls in place. With multiple vendors there are also potentially multiple places where source documents are being to stored.
1.11 |  |  | Are there appropriate validation and SDLC processes in place and transparent? | It is possible to get all information on controls, from security, privacy and quality management?
1.12 |  |  | Has due diligence been performed on all DCT third parties? | Has a vendor qualification audit taken place? Is vendor aware of, and able to demonstrate their GXP responsibilities? Risks may be higher with newly established niche vendors
1.13 |  |  | Does the DCT process add additional burden to the sites? | Consider number of DCT components in use and amount of software / hardware site has to utilize
2 | Trial Planning and Design | Trial design should be considered before developing the protocol and relevant stakeholders should be consulted in these discussions. | [6 empty] | 1
2.1 |  |  | What elements of the DCT differ from conducting the trial in a more traditional model? | Evaluate which elements of DCT methods /tools differ from a standard trial to identify new risk areas for evaluation. Include additional systems and vendors which may be in use and requirements for control and oversight. | [5 empty] | Have in place a specific data management plan/diagram for DCTs to show how the data flows and data ownership.
2.2 |  |  | Are there any additional safety risks associated with the planned decentralized processes? | Is it possible to conduct all protocol required assessments and IP management activities with remote alternatives? Consider that some investigations can only be effectively performed face to face. | [5 empty] | Determine and make clear in the protocol/participant information sheet / NCA & IEC submission which elements of the trial can be decentralized.
2.3 |  |  | Are the proposed decentralized approaches suitable for implementation in all geographical locations / with all participants? | Some DCT activities may only be accepted (culturally or per local regulations) in some countries and /or participant populations and may necessitate a 'hybrid approach' - this may introduce unintentional bias or risk e.g. rating scale administration may not be comparable between on-site and remote delivery | [5 empty] | Engage with all stakeholders as early as possible (see next section) to assess acceptability of proposed approaches. Consult with project biostatistician to assess the potential impact on data integrity / interpretability of utilizing a hybrid approach
2.4 |  |  | Are the proposed decentralized approaches likely to be accepted by the participant population? Taking into account the disease nature and participant population demographics? | Care needs to be taken not to unintentionally exclude participants from accessing a clinical trial because they are unable / uncomfortable with accessing DCT methods or technologies e.g. accessibility issues in some countries; elderly engagement with technology; impact on mental health | [5 empty] | Design communication models and scenarios; what these look like could depend on the trial, such as participant interfaces with investigators and health care professionals, call center models, video, phone, telemedicine, trial participant interacts or travels to a local site.
2.5 |  |  | Are there any relevant regional and / or national legal requirements and /or site requirements which may prevent implementation of proposed decentralized approaches on the trial? | Are there restrictions in planned countries for study conduct which will require a hybrid approach rather than fully decentralized approach and what is the impact of this? | [5 empty] | Consult with National Competent Authorities / IRBs/IECs and local site authorities to confirm acceptability of proposed methods prior to finalizing strategy and country list
2.6 |  |  | Is it clear how data will be collected and how it will flow between systems and parties involved in the conduct of the trial? Is a data flow diagram available to demonstrate this? | Consider who owns the data, where it will reside and who is responsible for long term archiving of data after study completion. Consider who will monitor /clean the data and how this oversight will be documented? Are there audit trails that can /should be reviewed, with a process to follow? Consider how Investigator maintains oversight and control of data related to participants from their site - Sponsor / vendor should not be able to change participant data independently from investigator and without their approval (unless an agreed self evident query) Consider who has edit /read access to data and how Investigator continued access will be assured during archiving period Consider how participant privacy is maintained e.g. requirements for firewall between investigator facing and Sponsor facing data; pseudonymization etc. Will data from all vendors be integrated into the EDC or will data exports be provided from each vendor for analysis purposes, and on what frequency? | [5 empty] | Schedule a meeting as early as possible in trial set up as possible with all vendors to agree and map data flow requirements and confirm monitoring strategy
2.7 |  |  | Are the new technologies fit for purpose and validated in line with computer systems validation principles? | Consider whether technology has been developed specifically for clinical trial /medical use or whether more generic apps are being utilized? If the latter do they meet all GXP requirements (e.g use of fitness trackers) | [5 empty] | Conduct vendor qualification audit before proceeding with any new technology vendor; develop a standard framework for qualification audits of vendors
2.8 |  |  | Is there any potential impact of the proposed technical solutions on data protection, data security and data privacy? | Consider where data resides - is it stored on a server within country or in a third country which may have different data privacy controls? Is technology specifically developed for clinical trials and have demonstrated GXP compliance or is the technology a generic commercial offering which may not have those controls built in?
3 | Early participant and Stakeholder Engagement | Early engagement with all stakeholders ensures study participants, investigator, and study sponsor are met as well as promoting a study design and strategy that is more likely to succeed. | Fiona/Brian | [5 empty] | 1
3.1 |  |  | Stakeholders (including trial participants, relevant third parties etc.) involvement to understand operational barriers to adoption and provide insight to specific expertise in support of downstream quality | Consider how to engage and communicate cross-functional stakeholders are/will be informed early in the process | [5 empty] | Analyze protocol procedures to evaluate which one can be decentralized.
3.2 |  |  | Consequences for participants; involve participant/participant association to review participant journey | Review how early engagement opportunities with participant advocacy groups will impact DCT protocol and strategy development | [5 empty] | Early engagement with relevant stakeholders such CROs and computer systems vendors who have developed these platforms will be important in determining strategy.
3.3 |  |  | Capabilities and qualification/validation of systems that will support DCT strategies | Perform early assessments of capabilities and qualifications of systems
4 | R&D Consultation and Peer Review | In the UK an NHS R&D Office must ensure all relevant approvals are in place before a research project can take place within their organization | [6 empty] | 1
4.1 |  |  | Have the processes and technologies been established to be provided in a timely manner for NHS R&D office review? | Are processes and technologies well understood and documented by R&D approvers.
5 | Protocol Development, Protocol Approval | All aspects of a DCT or hybrid trial should be described from the end to end perspective and special considerations need to be made to ensure that no additional risks to participants occur | [6 empty] | 1
5.1 |  |  | Will alignment with key stakeholders prior to finalization of the protocol be required? | Early engagement with key stakeholders is recommended during the protocol design to clear outline accountability and obligations. | [5 empty] | Engage with all stakeholders whom may be involved trial and building in feedback early on will subsequently help to avoid protocol amendments later on stakeholders will include for example CROs, regulators, MHRA.HRA and third parties and experienced vendors
5.2 |  |  | Does the protocol outline the accountable parties at each step in the supply chain, from the requisition to distribution to the study participant to destruction or return of used and unused study drug? | Evaluate delivery mechanisms for drug distribution, administration and return process for destruction of investigative product.
5.3 |  |  | Will different electronic systems and technologies by used? | If yes, consider the protocol outlining all electronics systems and technologies to be used in the study. Outline the types of technology solutions and mobile solutions to be used across the end to end DCT.
5.4 |  |  | Does the protocol outline how data will be collected and the timing? | The protocol should outline describe how data will be captured, frequency of data collection, the impact on the participant are critical to evaluate and address.
5.5 |  |  | Is documentation present for the relevant technologies and suitably validated? | Include additional risks there may be regarding DCTs in the risk benefit section of the protocol along with risk mitigation measures.
5.6 |  |  | Have any additional risks there may be regarding DCTs described in the risk benefit section of the protocol along with risk mitigation measures?
6 | Trial Monitoring and Management | Appropriate planning before the trial and adequate oversight and monitoring during the trial will help ensure that trial participant safety is maintained throughout the trial and that there is accurate reporting of results at its conclusion. | [6 empty] | 1
6.1 |  |  | Is there a process for provisioning to the trial participant and investigational sites? | Not all mobile technologies and apps are suitable to be used in a DCT. Ensure relevant technologies used are in line with data protection and privacy laws and regulations; Information security standards and/or applicable security laws (add references here) | [5 empty] | Outline responsibilities for 21CFR part 11 and UK compliance in regards to validation, UAT, back-up, licensing of applications used for the participant, sites and operations.
6.2 |  |  | How will data flow alter through wearables/devices and can this alter monitoring activities centrally? | Evaluate how monitoring will occur and the access to data for oversight.
6.3 |  |  | If home care nursing is being provided to participants what are the key interactions and how will information be shared between the site, homecare nurse and participants? | Determine data access and impact of roles defined within the technology. | [5 empty] | Onsite and remote monitoring to support reduced SDV/SDR strategies
6.4 |  |  | What systems require access for the site and investigator?
6.5 |  |  | Will notifications be distributed to the site and participants? | Consider expectations for supporting timely follow-up and roles and responsibilities.
6.6 |  |  | Is there a process for validation, UAT, back-up, licensing of applications used for monitoring activities?
7 | Trial Supplies | Appropriate procedures and controls need to be in place for Direct-to-participant and Direct-from-participant trial delivery/dispatch. | [6 empty] | 1
7.1 |  |  | Is the IP appropriate for home administration /storage? Will the IP be able to be stored within the required storage conditions at a participant's home without additional equipment? | Consider if the planned DTP/DFP deliveries are appropriate for use by the participant population, development stage and trial design. Consider if there are any safety / security risks of shipment to or storage of IP at participant's home e.g. cytotoxic substance, controlled drug, can the IP be stored at room temperature, household fridge or household freezer and remain within specification? Is there stability data to support this and also to support temperature excursions? What type of instructions would need to be provided to ensure that appropriate storage was used? (this is a similar scenario to current studies where IP is provided to participants for a cycle of treatment). Are there any considerations for IP administration and does it require to be administered by home healthcare professionals ? | [5 empty] | Clearly describe the supply and dispatch procedures either in the protocol and/or a study document for the investigator and home nurse. Also document in ICF or separate document for participant. These should include requirements for temperature monitoring during transportation, recording of temperature excursions and actions required if these occur or participant identifies IP as being damaged on receipt; also participant should be clearly aware of any specific storage / administration / return requirements for the IMP and able to comply with these, additional training may be required for self-administration or a home nurse can be used
7.2 |  |  | Does the supply chain process to provide the IP to the participant have appropriate approvals from the RA / EC in the participating countries? Have necessary EC / CA approvals for IP shipment process and any written information provided to participant to support handling of the IP. | Sufficient detail of the supply chain activities should be included in the CTA application to ensure that there is approval for the process. Also important to consider processes for receipt (including confirmation of completeness and stability on receipt), accountability, return and destruction as well as IP re-supply and that there are sufficient instructions for this to be completed by the study participant. | [5 empty] | Ensure that sufficient information is provided in the submitted CTA documents and appropriate training is provided to all stakeholders and documented.
7.3 |  |  | Consider specific safety concerns associated with the use of the supplies. Does the IP have any specific safety concerns to be considered before home storage and administration could be permitted safely? | Consider how any challenges have been identified and managed in prior investigational or marketing experience. Does this differ in any way from participant obtaining IP at their clinical visit and bringing home? | [5 empty] | Establish procedures for drug accountability/return/destruction and compliance
7.4 |  |  | Do the proposed supply chain activities comply with data privacy laws in all considered countries? | Do any of the steps within the supply chain require sharing of participant's information and details, and does the process adequately protect the data being shared? E.g. transparent in participant information sheet and consent received to share information with depot /courier Are mechanisms in place to ensure IP is only delivered to participant or their nominated representative (i.e. risk of being left with neighbor or on doorstep)? | [5 empty] | Develop standard language for inclusion in participant information sheet or separate document for obtaining consent to share personal information with vendor. Contract with specialist couriers for transport of IP to participant home to minimize risk inappropriate delivery
7.5 |  |  | Evaluate the national legal and regulatory compliance of planned supply chains. Do the planned supply chains meet all regulatory and legal requirements in each country to allow shipment of IP to participants? | Consider use of an experienced supply vendor for timely delivery and pick-up within the required storage conditions in all considered countries. Request examples of previous experience or complete some dry-runs to ensure vendor capabilities are sufficient. Examine contingency plans for temperature excursions, delays, unforeseen situations (accidents, travel issues, unable to locate destination).
7.6 |  |  | If a depot is used, are the contracting and logistical requirements suitable and sufficient to allow distribution of IP? | Does the depot for distribution of IP have appropriate authorizations and facilities to ensure they can provide a DtP/DfP service? Does the depot work with specialist couriers for transport of the IP (i.e to ensure chain of custody, stability etc) ? | [5 empty] | Work with specialist vendors in this area
8 | Trial Documentation and Trial Master File | A well-kept TMF is necessary for efficient trial management and to facilitate the reconstruction of the conduct of the trial during the audit/inspection process. | [6 empty] | 1
8.1 |  |  | Is it clear who is the responsible party for filing which documents into the TMF, and whether any secondary storage locations will be in used by any parties (both during the trial conduct and archiving period)? | Will all documents / data be sent to the TMF on an ongoing basis by all vendors or will any vendors retain responsibility for documents / data they create in a secondary location? E.g. data on vendor servers. | [5 empty] | Include details of who 'owns' the TMF elements in contract per EMA TMF Guidance Ensure the vendor contract details how to manage data when companies go through changes. such as bankruptcy
8.2 |  |  | Is it clearly documented which documents (if any) are stored in secondary locations are clearly detailed in the study TMF plan and vendor contracts as appropriate? | Where documents are held in a secondary location, determine how all parties given access to them as needed? Where everything is held in the TMF what processes are in place for the timely loading into the TMF and accessibility to all parties? | [5 empty] | Management and recording of the metadata Ensure Master TMF index details clearly where data is held, if in a secondary location outside of TMF and that contract or other project document outlines how parties needing access to that documentation during the study will have access; Also document plan for consolidation into TMF or long term storage at study closure
8.3 |  |  | How will Investigators retain responsibility for the management and oversight of documents generated outside their direct control and what procedures they have in place for their maintenance and retention? | Consider how investigator will obtain access to information from satellite sites (e.g.local medical doctors) or other local health care providers (e.g. local lab, imaging facility) and home visits by the study participants, clinical investigator, study personnel, or third-party contractors such as homecare nurses | [5 empty] | Develop site agreements when satellite sites /Homecare nurses in place which detail how source documentation will be managed
9 | Contracts and Agreements | Many parties may be involved in the conduct and management of a clinical trial. | [6 empty] | 1
9.1 |  |  | Will there be an impact to the site and investigating team for providing the care using technology? | Need to be very specific on roles and responsibilities of all parties involved in the DCT. Clarify where the contractual obligations lie. | [5 empty] | Maintain a central listing in organization of all different potential vendor types involved within the DCTs
9.2 |  |  | Is there clarity to responsibilities by CRO and sponsor for DCT elements? | Consider if there is a lack of clarity and responsibilities, major challenges have been highlighted by EU IWG.
10 | Ethics Submission | The Health Research Authority (HRA) facilitates ethical research that is of potential benefit to participants. The Research Ethics Service (RES) is a core function of the HRA. | [6 empty] | 1
10.1 |  |  | What is the process and transparency regarding what is being done remotely and who is involved? | The submission process itself will not change with DCTs. However, it is important that the submission package (protocol, ICF, scripts, storyboards and views of software applications) clearly outline the way in which the trial will be conducted - I.e. use of telemedicine, wearable technologies, use of e-consent, ePRO/eCOA forms, participant Portals, remote access to EHRs etc. | [5 empty] | Provide screen shots, videos or other evidentiary materials which outline any content or materials with which the participant will be presented.
10.2 |  |  | Are the relevant parties involved and aspects of the DCT made available to the ethics committee ensuring the process is well described and understandable? | [6 empty] | Provide a sample of the final product of approved materials once the system in ready to go live. This will include copies of the final production video for informed consent as well as a recorded demo of the data collection tools.
11 | Informed Consent | Participants must give their informed consent before being entered into a trial | [6 empty] | 1
11.1 |  |  | How is informed consent is administered and accessed? | Consideration of ICF being administered via video, electronically or via document and accessed via web-based portal, email for participant and site.
11.2 |  |  | What methods are used to positively identify the participant? | Evaluate how the participant identification will be confirmed and the overall process for the participant.
11.3 |  |  | What methods are used to obtain the participant’s signature? | Consider the patient burden with the overall process.
11.4 |  |  | How copies of informed consent are provided to the participant (by email, through an online portal, mailed)? | Consider responsibility and PHI consideration with automation.
11.5 |  |  | How are investigator/sub investigator planning to assess the participant’s understanding of the informed consent? | Evaluate if automation can be utilized to determine the level of understanding by the participant.
12 | Inspection & Audit | European legislation requires Member States to inspect organizations that hold clinical trials authorizations or conduct activities on behalf of the clinical trial sponsor | [6 empty] | 1
12.1 |  |  | Can all systems be accessed for the lifecycle of the study and after the study is archived? How long will they be archived? | Parties should be able to provide timely access to systems or data, this should be stipulated by contract. | [5 empty] | Contractual obligations must clearly define responsibilities that cover all required activities.
12.2 |  |  | How would complete and direct system access be ensured for Inspectors? | Parties should be able to provide timely access to systems or data, this should be stipulated by agreement, with appropriate user roles and access rights established. | [5 empty] | Provide project specific plans that were developed to mitigate risk (e.g. determine quality tolerance limit thresholds, align contractual agreements with plans).
12.3 |  |  | Availability of Critical data definition and identification, with documentation in place to show data flows and data ownership. For ‘new’ technologies, consider specific data management plans/diagrams (flow between Sponsor, Participant, Vendors, Site Staff, CRO (Data Management, Monitors etc.) - how would this be ensured? | Ability to comprehensively demonstrate integration, validation and user acceptance testing at platform level (e.g. data controlled during transit and at rest, audit and change history). | [5 empty] | Contracts – ensure availability and/or provision of documentation during and after the trial (i.e. specific provision and level of documentation for inspection purposes)
12.4 |  |  | How would it be demonstrated that new technologies have been assessed as fit for purpose and validated in line with computer systems validation principles? | Assessment package/documentation should include implications for areas such as data protection, data security and privacy, especially if the trial involves social media. | [5 empty] | Relevant responsible individuals (i.e., the investigator and DCT study personnel) should be available on site or by phone to answer any questions that may arise
12.5 |  |  | What additional controlled documents are in place for the oversight and management of decentralized clinical trials? | Enhanced controlled documents addressing data privacy, confidentiality and anonymization of personal data. | [5 empty] | Development of process workflows to outline activities from start-up through archiving.
12.6 |  |  | Equipment/Materials – how would availability be ensured at site/office of tools (and records of calibration, training etc.) used to perform remote activities (e.g. equipment used by Mobile Nurses)? | Parties should be able to provide timely access to equipment, systems or data, this should be stipulated by agreement. | [5 empty] | Ensure data pertaining to new service lines/solutions is tracked in a way that can be reported.
12.7 |  |  | How would the TMF be described? It should be ensured that companies identify all the systems that make up the TMF and ensure direct access for Inspectors. | Controlled documents could outline components involved decentralized clinical trial, as applicable. | [5 empty] | Demonstrate new systems or technologies to save time on training and issues with navigation
12.8 |  |  | Inspections may need to take place at other facilities (e.g., local clinics and pharmacies) where trial-related activities occurred, according to prior arrangements between the investigator and these facilities - how would this be catered for with regards to inspection planning? | Parties should be able to provide timely access to equipment, systems or data, this should be stipulated by agreement.
12.9 |  |  | How would PI oversight be demonstrated for all facilities or contracted parties? | PI should have documentation available demonstrating access, information required, received, and any follow-up activities performed.
13 | Archiving | The Clinical Trials Regulations and specifically, Regulation 31A of the Medicines for Human Use (Clinical Trials) Amendment Regulations 2006, define the archiving requirements for Clinical Trials of Investigational Medicinal Products (CTIMPs) | [6 empty] | 1
13.1 |  |  | How will investigators access the data during the trial and once the trial has closed? | How will collection of documents occur and will access to alternative storage locations be available (e.g. TMF index). Consider ALCOA+. | [5 empty] | Determine who is responsible for archiving which data and being very clear in the contract regarding the roles and responsibilities

## Drop-down Lists
Drop-down categories for Risk Assessmentr tab, Column F | Drop-down categories for Rusk Assessment tab, Column G | Drop-down categories for Risk Assessment tab, Column H | 3 point scale
High (3) | High (3) | Difficult to detect (3) | 3
Medium (2) | Medium (2) | Medium to detect (2) | 2
Low (1) | Low (1) | Easy to detect (1) | 1